## Sheet1
| Task | Sub task | Hr.
1 | Home page |  | 2
Show/hide login and logout links
2 | Product details |  | 5
|  | Update price based on size and color | 2
Update price when user update quantity using +/- buttons
3 | Payment gateway
|  | Update order status and make payment detail entry on payment getway response | 6
|  | Make payment from wallet | 4
4 | User history
|  | Show user order history on user profile page | 6
5 | Order return
|  | User can raise return request for placed order | 8
|  | Payment getway for refund amount | 2
6 | Order invoice
|  | make invoice for purchsed products | 4
7 | User profile page
|  | User can associate only activated referral | 2
8 | Admin
|  | Commision calculation (7%,8%,9%,10%,11%,12%) | 8
|  | Level based commision | 6
|  | Treeview layout update | 5
9 | Pickup master |  | 6
|  | Order detail for user | 4
Create challan report
10 | Reports
|  | Products reports | 4
|  | User reports | 4
|  | Sale products reports | 4
|  | Pickup master report | 4
| Total |  | 86